## Sheet1
Burn down chart
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
mencari informasi sumatera utara untuk introduction | Story 1 | Task 1.1 | 6 | 6 | 0 | 0 | 0 | 0
mencari informasi tentang brastagi | Story 1 | Task 1.2 | 6 | 3 | 0 | 0 | 0 | 0
mencari informasi tentang danau toba | Story 1 | Task 1.3 | 6 | 3 | 0 | 0 | 0 | 0
mencari informasi tentang bukit lawang | Story 1 | Task 2.1 | 6 | 3 | 0 | 0 | 0 | 0
mencari informasi sipiso-sipiso | Story 2 | Task 2.2 | 6 | 3 | 0 | 0 | 0 | 0
mencari informasi simalem | Story 3 | Task 3.1 | 6 | 0 | 0 | 0 | 0 | 0
mencari informasi istana maimun | Story 3 | Task 3.2 | 6 | 0 | 0 | 0 | 0 | 0
My Project | Story 3 | Task 3.3 | 6 | 0 | 0 | 0 | 0 | 0
My Project | Story 3 | Task 3.4 | 6 | 0 | 0 | 0 | 0 | 0
My Project | Story 4 | Task 4.1 | 6 | 0 | 0 | 0 | 0 | 0
My Project | Story 4 | Task 4.2 | 6 | 0 | 0 | 0 | 0 | 0
My Project | Story 4 | Task 4.3 | 6 | 0 | 0 | 0 | 0 | 0
My Project | Story 4 | Task 4.4 | 6 | 0 | 0 | 0 | 0 | 0
Ideal - Remaining efforts in uninterrupted working hours |  |  | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 60 | 18 | 0 | 0 | 0 | 0
Note on F3: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G3: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered